## Risk Register
DEVELOPMENT RISK REGISTER |  |  | XYZ |  |  | Rev 1 | Last Updated | 6th April 2020
Ref | Risk Description | Classification | Owner-ship | Risk Rating before Action Plan |  |  |  |  | Mitigation | Risk Rating after Action Plan |  |  | Residual Risk | Impact on Cost | Current Status | Status / Date Action Required
|  |  |  | Category | Probability | Impact | Consequences | Rating |  | Probability | Impact | Rating
1 | Main contractor over- run on costs through variations |  | Commercial Manager | Commercial | 2 | 1 | Cost base increases and funding not available from Development finance bank facility. Further funds required from developer/private investors | Green | Ensure full audit and sign off of cost plan and detailed design/performance pspecification prior to tender of main contractor contract. | 2 | 3 | Amber | Risk will remain and must be managed weekly through detailed tender and contract negotiation phase, weekly Requests for Information, Main contractor reports, drawdown schedules, variation schedules, contingency management and cashflow forecasting. | Moderate, however controllable | Tender documents being drafted and detailed design ready for final approval by 30 April. | 30/4/2020
2 |  |  |  |  | 1 | 1 |  | Green |  | 1 | 1 | Green
3 |  |  |  |  | 1 | 1 |  | Green |  | 1 | 1 | Green
4 |  |  |  |  | 1 | 1 |  | Green |  | 2 | 1 | Green
6 |  |  |  |  | 1 | 1 |  | Green |  | 2 | 1 | Green
7 |  |  |  |  | 1 | 1 |  | Green |  | 2 | 1 | Green
8 |  |  |  |  | 1 | 1 |  | Green |  | 2 | 1 | Green
9 |  |  |  |  | 1 | 1 |  | Green |  | 3 | 1 | Green
10 |  |  |  |  | 1 | 1 |  | Green |  | 1 | 1 | Green
11 |  |  |  |  | 1 | 1 |  | Green |  | 3 | 1 | Green

## Risk Matrix
Likelihood of non-conformance | Very High | 5 | 5 | 10 | 15 | 20 | 25
| High | 4 | 4 | 8 | 12 | 16 | 20
| Medium | 3 | 3 | 6 | 9 | 12 | 15
| Low | 2 | 2 | 4 | 6 | 8 | 10
| Very Low | 1 | 1 | 2 | 3 | 4 | 5
|  |  | 1 | 2 | 3 | 4 | 5
|  |  | Very Low | Low | Medium | High | Very High
Category |  |  | Consequence severity to categories
Q | Quality
S | Safety
F | Funding
C | Commercial
R | Resources
P | Programme
C | Internal Partners
Se | Security
E | Environmental
B | Business
Sa | Sales
De | Design